## Capital Needs
Your Church Name |  |  |  |  | 2013-06-04
Capital Needs List
| Capital Needs List | Quantity | Cost Per | Total cost | Description | Comments | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
1 | HVAC equipment | 7 | 75000 | 525000 | Replace old and inefficient equipment | as needed
2 | Roofs | 3 | 50000 | 150000 | Replace roofs and shingles | as needed
3 | Windows | 85 | 1000 | 85000 | Replace all windows and cover frames in vinyl |  | 2011: 8 doors; 39 windows; 2012: 20; 2013: 20; 2014: 20
4 | Paint | 1 | 75000 | 75000 | Repaint all walls in the church | as needed
5 | Children's furniture | 1 | 25000 | 25000 | Replace existing children's furniture | as able
6 | Children's bathrooms | 3 | 10000 | 30000 | Completely gut and replace with totally new furnishings | as able
7 | Exterior doors | 9 | 3000 | 27000 | Replace existing with aluminum doors |  | 2011: 8 class doors; 2012: 2 wood & class doors; 2013: classroom doors
8 | Carpet in Worship Center | 1 | 55000 | 55000 | Completely replace carpet in Commons |  | 2012: Fellowship Hall carpet
9 | 1st floor asbestos | 1 | 40000 | 40000 | Abate asbestos: replace ceilings and floor tiles |  | 2009: FH done; 2012: 1st floor - 4 kids' rooms; 2013: 1st floor - 4 kids' rooms
10 | 1st floor bathrooms | 4 | 10000 | 40000 | Completely gut and replace with totally new furnishings | as able
11 | 3rd floor bathrooms | 4 | 10000 | 40000 | Completely gut and replace with totally new furnishings | as able
12 | Worship Center chairs | 400 | 50 | 20000 | Buy chairs | as needed
13 | Playground equipment | 5 | 8000 | 40000 | Purchase and install several new pieces of equipment | as able
14 | Sanctuary Bathrooms | 4 | 10000 | 40000 | Completely gut and replace with totally new furnishings | as able | 2012: M/W by Parlor; 2013: M/W by bell room; 2014: M/W 3rd floor; 2015: M/W 3rd floor; 2016: M/W 1st floor
15 | Gutters | 1 | 30000 | 30000 | Install new gutters |  | 2009: small garden; 2010: sanctuary & northside; 2011: Buford Road downspouts; 2012: Elm Street; 2013: Elm Street; 2014: Maple Ave
16 | Hardscaping on Elm Street | 1 | 15000 | 15000 | Build terracing at Sanctuary entrance |  | 2015: hardscaping
17 | HVAC energy system | 1 | 30000 | 30000 | Install motion sensor stats |  | 2011: $7.5K for motion stats; 2012: $7.5K for motion stats; 2013: $7.5K for motion stats; 2014: $7.5K for motion stats
18 | Landscaping on Elm Street | 1 | 10000 | 10000 | Plant color beds on Forest Hill Ave. |  | 2011: Columbarium; 2012: Elm Street; 2013: Elm Street; 2014: Maple Ave
19 | Other bathrooms | 6 | 5000 | 30000 | Replace partitions and other items as needed; not to be gutted | as able
20 | Classroom furniture | 1 | 17000 | 17000 | Buy chairs and tables for adult rooms | as needed
21 | Lighting | 1 | 12000 | 12000 | Replace flourescents with energy saving T-8 tubes |  | 2010: replace; 2011: replace
22 | Lighting | 1 | 7000 | 7000 | Install flush mounted lights throughout |  | 2011: all hallways; 2012: all rooms
23 | Tile in hallways | 1 | 8000 | 8000 | 1st floor; 2nd & 3rd floor children's area; Sanctuary entrance |  | 2010: Sanctuary; 2013: children's halls; 2014: children's halls
24 | Motion sensors for lights | 1 | 9000 | 9000 | Install motion sensors through buildings |  | 2011: all hallways; 2012: bathrooms; 2013: classrooms
25 | Signage - interior | 1 | 6000 | 6000 | Completely redo all signage |  | 2012: 1st floor; 2013: half of 2nd floor; 2014: exterior; 2015: half of 2nd floor; 2016: 3rd floor
26 |  | 1
27 | Sanctuary Work
28 | Sanctuary platform | 1 | 250000 | 250000 | Reformat sanctuary platform and choir loft | capital campaign?
29 | Sanctuary Miscellaneous | 1 | 200000 | 200000 | Replace floor tile, improve HVAC, electric window shades | capital campaign?
30 | Sanctuary ceiling | 1 | 150000 | 150000 | Replace existing sanctuary ceiling, lighting, AV, etc. | capital campaign?
31 | Sanctuary asbestos | 1 | 100000 | 100000 | Abate asbestos | capital campaign?
32
33
34 | Completed Work
35 | Commons window shades | 6 | 1000 | 6000 | Install electric controls | done 2010 | 2010: done
36 | Gym window shades | 16 | 1000 | 16000 | Install electric controls | finished in 2012 | 2010: section 1; 2011: section 2; 2012: section 3
37 | Parking lot islands | 4 | 3000 | 12000 | Plant grass in all islands and put in crepe myrtles | done 2010 | 2010: remaining islands
38 | Landscaping on Elm Street | 1 | 4000 | 4000 | Plant azaleas and hydrangeas around Buford Road bldgs | done 2010 | 2010: porte cochere; 2011: Sanctuary entrance
39 | Lobby flooring | 1 | 22000 | 22000 | Completely replace carpet in lobby with tile | done 2010 | 2010: done
40 | Keys | 1 | 5000 | 5000 | Rekey entire building | done 2010
41 | Windows | 39 | 850 | 33150 | Replace all windows and cover frames in vinyl | partly done in 2011
42 | Exterior doors | 8 | 3000 | 24000 | Replace existing with aluminum doors | partly done in 2011
43 | Commons platform | 1 | 25000 | 25000 | Reformat platform | done in 2011
44
Note on B1: Steve Law: Replace all data with your own church's data. The data in this spreadsheet is for illustrative purposes only.
Note on B10: Steve Law: All bathrooms
Note on J11: Steve Law: $10,000
Note on K11: Steve Law: $10,000
Note on K12: Steve Law: $15,000
Note on J13: Steve Law: $15,000
Note on B14: Steve Law: Across from 126 and the small kitchen
Note on B15: Steve Law: Bathrooms beside rooms 313 and across from 318
Note on B18: Steve Law: Four bathrooms on either side of the sanctuary
Note on J18: Steve Law: $20,000
Note on K18: Steve Law: $20,000
Note on I19: Steve Law: $10,000
Note on L19: Steve Law: $8,000
Note on J22: Steve Law: $8,000
Note on B23: Steve Law: Bathrooms across from 100, choir suite, and 346-350
Note on I25: Steve Law: $5,000
Note on J25: Steve Law: $5,000
Note on J26: Steve Law: $5,000
Note on K26: Steve Law: $5,000
Note on B27: Steve Law: Replace existing carpet in hallways with vinyl tile
Note on J28: Steve Law: $5,000
Note on K28: Steve Law: $5,000
Note on I29: Steve Law: $3,000
Note on J29: Steve Law: $5,000
Note on K29: Steve Law: $3,000
Note on L29: Steve Law: $5,000